## project
Gaant Chart
Wireless Protocol | Jerry Jia (JJ), Oscar Kwan (OK), Alvin Man (AM), Jaegar Sarauer (JS) | [9 empty] | Oscar Kwan | [5 empty] | Jerry Jia |  |  |  |  | Jaegar Sarauer | [5 empty] | Alvin Man
| AUTHOR | DAYS | START | FINISH | ACTUAL |  | MONTHS
ACTIVITY |  |  | DATE | DATE | DURATION |  | NOVEMBER 9-15 | [7 empty] | NOVEMBER 16-22 | [6 empty] | NOVEMBER 23-30 | [5 empty] | DECEMBER 1-2
[6 empty] | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W
Documentation
Gaant Chart | OK | 16 | 2015-11-15 | 2015-12-01 | bar: NOVEMBER 9-15 S to NOVEMBER 23-30 SU
State Chart Diagram | OK + JJ + AM | 8 | 2015-11-11 | 2015-11-18 | bar: NOVEMBER 9-15 W to NOVEMBER 16-22 W
Pseudo Code | OK + JJ + AM | 8 | 2015-11-11 | 2015-11-18 | bar: NOVEMBER 9-15 W to NOVEMBER 16-22 W
Code documentation | OK + JJ + AM + JS | 16 | 2015-11-15 | 2015-12-01 | bar: NOVEMBER 9-15 S to NOVEMBER 23-30 SU
Programming
Connect to comm port | JS | 1 | 2015-11-18 | 2015-11-18 | bar: NOVEMBER 16-22 W
File Loader | JS | 8 | 2015-11-13 | 2015-11-20 | bar: NOVEMBER 9-15 F to NOVEMBER 16-22 F
Build Window | JS | 6 | 2015-11-13 | 2015-11-18 | bar: NOVEMBER 9-15 F to NOVEMBER 16-22 W
Command mode (WndProc) | JS | 16 | 2015-11-15 | 2015-12-01 | bar: NOVEMBER 9-15 S to NOVEMBER 23-30 SU
Engine Write Thread Start | JJ | 3 | 2015-11-18 | 2015-11-20 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 F
Engine Read Thread Start | JJ | 3 | 2015-11-18 | 2015-11-20 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 F
Idle | JJ | 6 | 2015-11-18 | 2015-11-23 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 M
Acknowledge Line | AM | 6 | 2015-11-18 | 2015-11-23 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 M
Wait for data | AM | 6 | 2015-11-18 | 2015-11-23 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 M
Packet check | AM | 6 | 2015-11-18 | 2015-11-23 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 M
Acknowledge Package | AM | 6 | 2015-11-18 | 2015-11-23 | bar: NOVEMBER 16-22 W to NOVEMBER 16-22 M
Receiver side: Check Priority State | OK | 3 | 2015-11-21 | 2015-11-23 | bar: NOVEMBER 16-22 S to NOVEMBER 16-22 M
Confirm Line | OK | 6 | 2015-11-23 | 2015-11-28 | bar: NOVEMBER 16-22 M to NOVEMBER 23-30 S
Wait for ACK | OK | 6 | 2015-11-23 | 2015-11-28 | bar: NOVEMBER 16-22 M to NOVEMBER 23-30 S
Send Data (create packet) | JJ | 6 | 2015-11-23 | 2015-11-28 | bar: NOVEMBER 16-22 M to NOVEMBER 23-30 S
Wait for Packet ACK | JJ | 6 | 2015-11-23 | 2015-11-28 | bar: NOVEMBER 16-22 M to NOVEMBER 23-30 S
Sender side: Check Priority State | OK | 5 | 2015-11-25 | 2015-11-29 | bar: NOVEMBER 23-30 W to NOVEMBER 23-30 SU
Display statistics | OK | 5 | 2015-11-25 | 2015-11-29 | bar: NOVEMBER 23-30 W to NOVEMBER 23-30 SU
Final Testing
Regression testing for all test cases | OK + JJ + AM + JS | 3 | 2015-11-29 | 2015-12-01 | bar: NOVEMBER 23-30 SU to DECEMBER 1-2 T
Test Case Documentation | OK + JJ + AM + JS | 3 | 2015-11-29 | 2015-12-01 | bar: NOVEMBER 23-30 SU to DECEMBER 1-2 T
*all are estimated planned times